## Risk Register
Risk ID | Risk Category | Risk Description | Likelihood | Impact | Severity | Recommended Mitigation | Risk Owner | Target Date | Status
VR-01 | Incident Response | Vendor does not provide a formally documented customer incident notification SLA. Delayed notification could impact enterprise response coordination during a security event. | Medium | High | High | Establish contractual breach notification requirements and escalation timelines. | Vendor Security Team | 2026-06-15 | Open
VR-02 | Data Governance | Vendor lacks a documented data retention and destruction policy for enterprise customer data. | Medium | Medium | Medium | Require documented retention schedules and secure data disposal procedures. | Compliance Team | 2026-06-22 | Open
VR-03 | Third-Party Oversight | Limited visibility into subcontractor and subprocessor security governance controls. | Medium | Medium | Medium | Request annual security attestations and subprocessor inventory documentation. | Vendor Management Office | 2026-06-30 | Open
VR-04 | Vulnerability Management | Vendor performs vulnerability scanning but remediation timelines are not formally defined or tracked. | Low | Medium | Low | Require documented remediation SLAs based on vulnerability severity levels. | Security Operations | 2026-06-18 | Open
VR-05 | Access Management | Privileged access reviews are performed inconsistently across administrative accounts. | Medium | High | High | Implement quarterly privileged access reviews and approval workflows. | Identity & Access Management Team | 2026-06-20 | In Progress
VR-06 | Logging & Monitoring | Log retention standards were not clearly documented during the assessment process. | Low | Medium | Low | Define centralized logging retention requirements and monitoring procedures. | Security Engineering | 2026-06-25 | Open
VR-07 | Business Continuity | Business continuity testing evidence was not provided for review. | Medium | Medium | Medium | Request annual disaster recovery and business continuity test results. | Vendor Risk Management Team | 2026-07-01 | Open
VR-08 | Compliance Documentation | Vendor SOC 2 report was outdated and did not reflect the current assessment year. | Low | Medium | Low | Obtain updated SOC 2 Type II report during annual reassessment cycle. | Compliance Team | 2026-06-28 | Open
VR-09 | Data Privacy | Data residency and cross-border transfer controls were not fully documented for international operations. | Medium | High | High | Perform privacy and legal review for international data processing requirements. | Privacy Office | 2026-07-05 | Open
VR-10 | Security Awareness | Vendor security awareness training cadence for employees was not documented. | Low | Low | Low | Request evidence of annual security awareness training completion. | Human Resources Security Liaison | 2026-07-10 | Open
This remediation tracking register was developed as part of a simulated enterprise vendor risk assessment portfolio exercise intended to demonstrate governance, risk management, and information security remediation workflows.

## Remediation Tracking
Risk ID | Risk Description | Remediation Action | Assigned Owner | Target Completion Date | Current Status | Validation Method | Notes
VR-01 | No formal customer incident notification SLA | Establish contractual incident notification timelines and escalation procedures within vendor agreement. | Vendor Security Team | 2026-06-15 | Open | Review updated contract language and SLA documentation | Requires Legal and Procurement review prior to onboarding approval
VR-02 | Undefined data retention and destruction policy | Obtain documented data retention schedule and secure disposal procedures from vendor. | Compliance Team | 2026-06-22 | Open | Validate approved retention policy documentation | Policy must align with enterprise data governance standards
VR-03 | Limited subprocessor oversight visibility | Request annual subprocessor inventory and third-party security attestation reports. | Vendor Management Office | 2026-06-30 | Open | Review SOC 2 reports and vendor oversight documentation | Additional review required for international subprocessors
VR-04 | Undefined vulnerability remediation timelines | Implement documented remediation SLAs based on vulnerability severity ratings. | Security Operations | 2026-06-18 | In Progress | Validate remediation workflow and SLA documentation | Quarterly reporting cadence recommended
VR-05 | Inconsistent privileged access reviews | Establish quarterly privileged access certification and approval reviews. | Identity & Access Management Team | 2026-06-20 | In Progress | Review access certification records and audit evidence | Focus on administrative and service accounts
VR-06 | Log retention standards not documented | Define centralized logging retention requirements and monitoring standards. | Security Engineering | 2026-06-25 | Open | Review logging configuration and retention policy documentation | Align retention period with enterprise policy requirements
VR-07 | Business continuity testing evidence unavailable | Obtain disaster recovery and business continuity testing evidence from vendor. | Vendor Risk Management Team | 2026-07-01 | Open | Validate test reports and recovery exercise documentation | Annual reassessment recommended
VR-08 | Outdated SOC 2 report provided | Request updated SOC 2 Type II report covering current assessment period. | Compliance Team | 2026-06-28 | Open | Review updated independent audit documentation | Ensure report scope includes production systems
VR-09 | Data residency controls not fully documented | Conduct privacy and legal review of international data transfer practices. | Privacy Office | 2026-07-05 | Open | Validate privacy impact assessment and transfer safeguards | Additional contractual clauses may be required
VR-10 | Security awareness training evidence unavailable | Request annual security awareness training completion metrics and policy documentation. | Human Resources Security Liaison | 2026-07-10 | Open | Review training records and awareness program materials | Include phishing simulation metrics if available

## Severity Definitions
Severity Level | Definition | Business Impact | Response Requirement | Example Scenario
Low | Minimal security, operational, or compliance exposure with limited business impact. Existing controls are generally sufficient to manage the risk. | Limited operational disruption or low likelihood of data exposure. | Address through standard remediation processes and monitor during routine review cycles. | Missing documentation for employee security awareness training records.
Medium | Moderate risk exposure that could impact business operations, regulatory obligations, or information security if not addressed in a reasonable timeframe. | Potential operational disruption, limited compliance exposure, or increased likelihood of security incidents. | Mitigation activities should be prioritized and tracked with defined remediation timelines. | Undefined data retention policy for customer information.
High | Significant risk exposure that could result in major operational disruption, regulatory impact, reputational damage, or compromise of sensitive data. | High likelihood of business disruption, security breach, compliance violation, or customer impact. | Immediate remediation or compensating controls required prior to production approval or continued vendor engagement. | No formal incident notification SLA for security breaches involving customer data.
Critical | Severe risk exposure presenting an immediate threat to business operations, sensitive data, or regulatory compliance. Risk may require suspension of vendor onboarding or emergency escalation procedures. | Potential for catastrophic

## Definitions Cont'd
Status Definitions |  | Remediation Status Definitions |  | Validation Guidance
Status | Definition | Status | Definition | Validation Type | Description
Open | Risk identified and awaiting remediation activity | Open | Remediation activity has not yet started | Documentation Review | Review of policies, procedures, contracts, or audit evidence
In Progress | Remediation activities actively underway | In Progress | Remediation work is actively underway | Technical Validation | Verification of implemented technical controls
Mitigated | Risk reduced through implemented controls | Mitigated | Control improvements implemented and awaiting validation | Control Testing | Testing of operational effectiveness for implemented safeguards
Closed | Risk remediation completed and validated | Closed | Remediation validated and risk formally resolved | Audit Evidence Review | Independent evidence review supporting remediation completion
Accepted | Risk formally acknowledged and accepted by management | Accepted | Risk formally acknowledged and accepted by management
This remediation tracking register was developed as part of a simulated enterprise vendor risk assessment portfolio exercise intended to demonstrate governance, risk management, and information security remediation workflows.